PROJECT PLANNING PHASE

PocketSmart AI

Project documentation prepared from the uploaded PocketSmart AI source code and the supplied project-phase templates.

# 1. Planning Overview

PocketSmart AI is planned as an AI-assisted budgeting and recommendation web application. The planning phase converts the implemented features into Agile epics, user stories, story points, sprint goals, and measurable completion criteria.

# 2. Product Goal

Provide authenticated users with practical, budget-aware recommendations for home interior planning, party/event planning, and jewellery selection, while retaining generated plans for later review.

# 3. Product Backlog

| Epic | Story | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- |
| Authentication | US-01 | Register with username, email and password | 3 | High |
| Authentication | US-02 | Log in and maintain a secure session | 2 | High |
| Authentication | US-03 | Log out and invalidate the application session | 1 | High |
| Dashboard | US-04 | View plan totals and category counts | 3 | Medium |
| Home Planner | US-05 | Enter budget, style, rooms and item quantities | 5 | High |
| Home Planner | US-06 | Generate a budget-aware home recommendation | 5 | High |
| Party Planner | US-07 | Enter budget, guests, event, venue and city | 3 | High |
| Party Planner | US-08 | Generate a budget-aware party recommendation | 5 | High |
| Jewellery Planner | US-09 | Enter jewellery preferences and optional outfit image | 5 | High |
| Jewellery Planner | US-10 | Generate jewellery recommendations with image support | 5 | High |
| Recommendations | US-11 | View recommendation details and source | 3 | High |
| History | US-12 | Filter, review and delete saved recommendations | 5 | High |
| AI/Fallback | US-13 | Use Gemini when available and fallback rules when unavailable | 5 | High |
| Security | US-14 | Prevent access to another user's recommendations | 3 | High |

# 4. Sprint Planning

| Sprint | Goal | Stories | Planned Points | Duration |
| --- | --- | --- | --- | --- |
| Sprint 1 | Authentication & Core Setup | US-01 to US-04 | 14 | 6 days |
| Sprint 2 | Home & Party Planning | US-05 to US-08 | 18 | 6 days |
| Sprint 3 | Jewellery, AI & Image Handling | US-09 to US-10, US-13 | 15 | 6 days |
| Sprint 4 | History, Security, Testing & Release | US-11, US-12, US-14 + tests | 16 | 6 days |

# 5. Sprint Schedule

| Sprint | Timeline | Major Activities |
| --- | --- | --- |
| Sprint 1 | Day 1–6 | Project setup, database, registration, login, JWT, dashboard basics |
| Sprint 2 | Day 7–12 | Home planner, party planner, validation, budget calculations |
| Sprint 3 | Day 13–18 | Jewellery planner, image validation/processing, Gemini integration, fallback |
| Sprint 4 | Day 19–24 | History, ownership checks, API/session tests, performance review, demo preparation |

# 6. Velocity and Burndown Plan

Using the supplied planning-template method, the planned total is 63 story points across four sprints. Planned average velocity = 63 ÷ 4 = 15.75 story points per sprint (approximately 16).

| Checkpoint | Planned Remaining Points |
| --- | --- |
| Start | 63 |
| End Sprint 1 | 49 |
| End Sprint 2 | 31 |
| End Sprint 3 | 16 |
| End Sprint 4 | 0 |

# 7. Definition of Done

Feature is implemented in the FastAPI application and linked to the appropriate UI.

Inputs are validated and invalid requests return a clear error response.

Authenticated features require a valid session/token.

Recommendation data is saved with the authenticated user's ID.

AI failures or invalid AI output do not break the planner; the fallback engine is used.

Automated tests are added for the major flow and security cases.

Documentation and demonstration steps are updated before release.

# 8. Planning Risks and Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gemini API unavailable | Recommendations may not be AI-generated | Use the built-in rule-based fallback and clearly label source. |
| Invalid or unsafe AI URLs | Incorrect external links | Use canonical HTTPS links for supported platforms instead of trusting model URLs. |
| Image upload issues | Jewellery planner may fail | Validate type/size and normalize supported images before processing. |
| Unauthorized record access | Privacy/data leakage | Use user_id ownership checks on recommendation reads/deletes. |
| Schedule overrun | Testing/demo may be delayed | Prioritize core planner flows and authentication before enhancements. |

# 9. Planning Deliverables

Product backlog

Sprint plan and tracker

Velocity/burndown plan

Definition of Done

Risk register

Release/demo checklist